## VISION
Exploration of GITHUB
Developers
Nagiri Rajeev
K Pradeep Kumar
Sameena A Rahiman
Duration : 25 Man hours(Max)

## Prodcut Backlog
Story | Story Points(1 to 5) | Sprint # | Status | Comments
Tutorial on GIT&GITHUB |  | 1 | Close
Understanding Requirements |  | 1 | Close | Discussion on what all the tasks will be involved for development of GIT
What is Version Control system? |  | 1 | Close
Why we need version control system? |  | 1 | Close
Avaialble version control tools how git is different from others |  | 2 | Open
What is GIT and GIT HUB? |  | 2 | Open
GIT&GITHUB Architecture |  | 2 | Open
Features of GIT |  | 2 | Open
What is central Repository and Local Repository? |  | 2 | Open
GIT Operations and Commands |  | 3 | Open
Creating Central Repositories-Commit Command |  | 3 | Open
Creating Local Repositiories |  | 3 | Open
Creating Project in Local And Central |  | 3 | Open
What is GIT GUI,GIT CMD and GIT BASH |  | 4 | Open
Make use of GIT BASH using GIT Init in Local |  | 4 | Open
Synchronozing Local Repository and Central Repository Using Commands |  | 4 | Open
Making Changes |  | 4 | Open
Parallel Development |  | 4 | Open
GIT Flow |  | 4 | Open
Examples |  | 4 | Open
FINAL PPT |  | 4 | Open

## SPRINT1(22-25 May)
S. No. | Task | Priority | Target date | Sprint # | Owner | Status | Comments
1 | Tutorial on GIT&GITHUB | 1 | 2017-05-24 | 1 | Rajeev,Pradeep,Sameena | Closed
2 | List out topics from watched video | 2 | 2017-05-24 | 1 | Rajeev,Pradeep,Sameena | Closed
3 | Any other sources to explore | 3 | 2017-05-25 | 1 | Rajeev,Pradeep,Sameena | Closed
4 | Splitting it as tasks(Preparation of Sprint2) | 2 | 2017-05-25 | 1 | Rajeev,Pradeep,Sameena | Closed
5 | What is Version Control system? | 2 | 2017-05-25 | 1 | Rajeev,Pradeep,Sameena | Closed
6 | Why we need version control systems? | 2 | 2017-05-25 | 1 | Rajeev,Pradeep,Sameena | Closed

## SPRINT2(26-31 May)
S. No. | Task | Priority | Target date | Sprint # | Owner | Status | Comments
1 | Avaialble version control tools and how git is different from others | 3 | 2017-05-26 | 2 | Rajeev,Pradeep,Sameena | Closed | Need to explore more on this topic
2 | What is GIT and GIT HUB | 1 | 2017-05-26 | 2 | Rajeev,Pradeep,Sameena | Closed
3 | GIT&GITHUB Architecture | 1 | 2017-05-29 | 2 | Rajeev,Pradeep,Sameena | Closed
4 | Features of GIT | 2 | 31_May | 2 | Rajeev,Pradeep,Sameena | Closed
5 | What is central Repository and Local Repository | 1 | 2017-05-29 | 2 | Rajeev,Pradeep,Sameena | Closed

## SPRINT3(1-6 Jun)
S. No. | Task | Priority | Target date | Sprint # | Owner | Status | Comments
1 | GIT Operatios and Commands |  | 2017-06-01 | 3 | Sameena | Closed
2 | Creating Central Repositories-Commit Command |  | 2017-06-02 | 3 | Rajeev | Closed
3 | Creating Local Repositiories |  | 2017-06-02 | 3 | Rajeev | Closed
4 | Creating Project in Local And Central |  | 2017-06-05 | 3 | Rajeev | Closed
5 | What is GITUI & GIT BASH |  | 2017-06-02 | 3 | Sameena | Closed
6 | Make use of GIT BASH using GIT Init in Local |  | 2017-06-06 | 3 | Sameena | Closed

## SPRINT4(7 -13Jun)
S. No. | TASK | Priority | Target Date | Sprint # | Owner | Status | Comments
1 | Synchronizing Local Repository and Central Repository Using Commands:GIT PUSH & GIT PULL |  | 2017-06-07 | 4 | Sameena | Closed
2 | Making Changes : GIT Status,GIT ADD,GIT COMMIT |  | 2017-06-08 | 4 | Pradeep | Open
3 | Parallel Development : BRANCHING,MERGING,REBASSING |  | 2017-06-08 | 4 | Pradeep | Open | Issue with Pulling requests from two origin's at a time,Should look into more on this-While creating folders we can create multiple folders for multiple orgins
4 | GIT Flow |  | 2017-06-09 | 4 | Pradeep | Open
5 | Examples |  | 2017-06-12 | 4 | Rajeev,Sameena,Pradeep | Yet to start | Try with different examples - Tableau files and Cognos Framework Manager files
6 | FINAL PPT |  | 2017-06-13 | 4 | Rajeev,Sameena,Pradeep | Yet to start